## MVP Overview
Cooking Oil & Ghee Agency Software — 4-Day AI-Assisted MVP
Project Field | Value | Day | Goal | Task Count | Completion % | Release Gate
Start Date | 2026-07-17 | Day 1 | Foundation, auth and products | 6 | 0% | App shell + product CRUD
Target MVP Date | 2026-07-20 | Day 2 | Inventory, purchases and parties | 6 | 0% | Stock updates from purchase
Total Tasks | 25 | Day 3 | POS, khata and invoice | 6 | 0% | Cash/credit sale works
Completed | 0 | Day 4 | Returns, cashbook, reports and QA | 7 | 0% | Complete demo workflow
In Progress | 0
Blocked | 0 | Hard rule for 4-day delivery
Overall Progress | 0% | Do not build full accounting, cloud sync or FBR inside these four days.
Use AI for schema, CRUD scaffolding, UI components, tests and seed data.
Developer must manually verify stock, khata and payment calculations.
Use one agency, one computer and one database for the first pilot.
A demo-ready MVP is possible; a polished market-ready ERP is not.

## 4-Day Task Plan
Task ID | Day | Module | Task Details | Execution | Priority | Status | Start Date | Due Date | Est. Hours | Progress % | Deliverable | Notes
D1-01 | Day 1 | Project setup | Create Electron/Next.js or desktop-web shell, database setup, environment config | AI + Developer | Critical | Not Started | 2026-07-17 | 2026-07-17 | 2 | 0% | Running app shell
D1-02 | Day 1 | Database schema | Create core schema: users, products, customers, suppliers, sales, purchases, ledger, stock movements | AI + Backend | Critical | Not Started | 2026-07-17 | 2026-07-17 | 3 | 0% | Core migrations
D1-03 | Day 1 | Login and roles | Owner, Admin and Cashier login with basic role checks | AI + Full Stack | High | Not Started | 2026-07-17 | 2026-07-17 | 2 | 0% | Working authentication
D1-04 | Day 1 | App navigation | Create sidebar, header and routes for main modules | AI + Frontend | High | Not Started | 2026-07-17 | 2026-07-17 | 2 | 0% | Usable navigation
D1-05 | Day 1 | Product CRUD | Product, category, brand, unit, barcode, prices and opening stock on one screen | AI + Full Stack | Critical | Not Started | 2026-07-17 | 2026-07-17 | 4 | 0% | Product management
D1-06 | Day 1 | Seed and test data | Generate realistic oil and ghee sample products, customers and suppliers | AI | Medium | Not Started | 2026-07-17 | 2026-07-17 | 1 | 0% | Demo dataset
D2-01 | Day 2 | Packing conversion | Support carton and piece conversion using smallest-unit stock storage | AI + Backend | Critical | Not Started | 2026-07-18 | 2026-07-18 | 4 | 0% | Carton/piece stock works
D2-02 | Day 2 | Stock engine | Create stock movement ledger for opening, purchase, sale, return and adjustment | AI + Backend | Critical | Not Started | 2026-07-18 | 2026-07-18 | 4 | 0% | Reliable stock ledger
D2-03 | Day 2 | Supplier CRUD | Supplier details, opening balance and outstanding balance | AI + Full Stack | High | Not Started | 2026-07-18 | 2026-07-18 | 2 | 0% | Supplier module
D2-04 | Day 2 | Purchase entry | Cash/credit purchase, carton/piece quantity, rate and stock update | AI + Full Stack | Critical | Not Started | 2026-07-18 | 2026-07-18 | 4 | 0% | Purchase workflow
D2-05 | Day 2 | Batch and expiry basic | Batch number, expiry date, near-expiry flag and expired-sale block | AI + Backend | High | Not Started | 2026-07-18 | 2026-07-18 | 3 | 0% | Basic expiry control
D2-06 | Day 2 | Customer CRUD | Customer, business, phone, type, opening balance and credit limit | AI + Full Stack | High | Not Started | 2026-07-18 | 2026-07-18 | 2 | 0% | Customer module
D3-01 | Day 3 | POS screen | Barcode/product search, cart, quantity, carton/piece and customer selection | AI + Frontend | Critical | Not Started | 2026-07-19 | 2026-07-19 | 5 | 0% | Fast POS UI
D3-02 | Day 3 | Sale posting | Cash and credit sale with automatic stock deduction | AI + Backend | Critical | Not Started | 2026-07-19 | 2026-07-19 | 4 | 0% | Sales workflow
D3-03 | Day 3 | Khata ledger | Customer debit/credit ledger, payment received and current balance | AI + Full Stack | Critical | Not Started | 2026-07-19 | 2026-07-19 | 4 | 0% | Customer khata
D3-04 | Day 3 | Supplier ledger | Supplier payable ledger and payment entry | AI + Full Stack | High | Not Started | 2026-07-19 | 2026-07-19 | 3 | 0% | Supplier khata
D3-05 | Day 3 | Discount approval | Cashier discount limit with owner PIN override | AI + Full Stack | Medium | Not Started | 2026-07-19 | 2026-07-19 | 2 | 0% | Discount control
D3-06 | Day 3 | Invoice print | Basic thermal invoice and browser/PDF print | AI + Frontend | High | Not Started | 2026-07-19 | 2026-07-19 | 3 | 0% | Printable invoice
D4-01 | Day 4 | Sales return | Partial/full sales return with stock and customer balance adjustment | AI + Full Stack | High | Not Started | 2026-07-20 | 2026-07-20 | 3 | 0% | Sales return flow
D4-02 | Day 4 | Damaged/expired stock | Simple stock loss entry with reason and quantity | AI + Full Stack | High | Not Started | 2026-07-20 | 2026-07-20 | 2 | 0% | Loss stock entry
D4-03 | Day 4 | Cashbook basic | Opening cash, expenses, recovery, supplier payment and closing cash | AI + Full Stack | Critical | Not Started | 2026-07-20 | 2026-07-20 | 4 | 0% | Daily cashbook
D4-04 | Day 4 | Essential reports | Daily sales, purchases, stock, customer ledger, supplier ledger, expenses and cashbook | AI + Full Stack | Critical | Not Started | 2026-07-20 | 2026-07-20 | 5 | 0% | Core reports
D4-05 | Day 4 | Dashboard alerts | Invoice count, low stock, expiry, pending customer and supplier balances | AI + Frontend | Medium | Not Started | 2026-07-20 | 2026-07-20 | 2 | 0% | Operational dashboard
D4-06 | Day 4 | Testing and fixes | Run complete purchase-sale-return-khata workflow and fix blockers | Developer + AI | Critical | Not Started | 2026-07-20 | 2026-07-20 | 4 | 0% | Usable MVP build
D4-07 | Day 4 | Demo packaging | Create demo login, sample data, backup file and installation notes | AI + Developer | High | Not Started | 2026-07-20 | 2026-07-20 | 2 | 0% | Demo-ready MVP

## MVP Scope
Module | Included in 4-Day MVP | Notes
Login & Roles | Yes | Owner, Admin, Cashier; basic permissions only
Dashboard | Yes | Operational alerts only; no profit/cash totals
Products | Yes | CRUD, barcode, retail/wholesale price, opening stock
Carton & Piece | Yes | One packing level per product; smallest-unit inventory
Inventory | Yes | Stock movement, low stock, adjustments
Batch & Expiry | Basic | Batch and expiry entry; simple near-expiry and sale block
Purchases | Yes | Cash/credit purchase and stock update
Suppliers | Yes | CRUD, balance and ledger
POS | Yes | Cash/credit sale, barcode search, carton/piece
Customers & Khata | Yes | Credit sale, payment, ledger, credit limit warning
Returns | Basic | Sales return only in core MVP
Damaged/Expired Stock | Basic | Simple adjustment with reason
Cashbook | Basic | Opening, inflow, outflow and closing
Reports | Basic | Daily sales, purchase, stock, ledgers, expenses, cashbook
Printing | Basic | Thermal/browser/PDF invoice
FBR | No | Architecture placeholder only; integration after MVP
Cloud Sync | No | Local backup first; sync added after pilot
Full Accounting | No | P&L, trial balance and balance sheet later

## After MVP
Priority | Feature | Recommended Timing
1 | Pilot feedback and bug fixes | Immediately after 4-day MVP
2 | Purchase return and exchange flows | Week 2
3 | Advanced pricing and customer-specific rates | Week 2
4 | Cloud backup and multi-device sync | Week 2-3
5 | FBR sandbox and production integration | After current FBR/integrator requirements are confirmed
6 | Advanced reports and profitability | Week 3
7 | Full accounting and journal entries | Later paid version
8 | Multi-branch and godown transfer | Later paid version

## Lists
Status | Priority | Execution
Not Started | Critical | AI
In Progress | High | Developer
Blocked | Medium | AI + Developer
In Review | Low | AI + Backend
Completed |  | AI + Frontend
On Hold |  | AI + Full Stack
Cancelled |  | Developer + AI